SECOND MEETING OF ECO-PCCM

Belgrade, 7-8.04.2005

CONCLUSIONS

Fiber selection:Kenaf, Cotton, Cellulose, Rice straw

Polymer matrix:PLA, PHB, PHBV, Starch’thermoplastic

Partners tasks for the next sixth months of WP1 and first 3months of WP2

- ICTP – Research on Kenaf-PLA composites, Mater B,

delivering of PLA, Mater B, PHB, PHBV, etc to TMF

- CIDEMCO-  Ageing, Mechanical and fire-retardant testing of NFC delivered by KEFI and ICTP, delivering samples to IP-BAS (Bulgaria)

- MONDIRECT- Set-up of the machinery that could be used for production of NFC, preparation of lab-scale samples of PLA-Rice straw

- KEFI – Delivering of  Kenaf-PLA preforms to all partners , Delivering of price list for PLA fibers as well as for the Kenaf based preforms to MOEPP and TMF-Skopje

- TMF – Investigation of eco-friendly composites on  lab-scale based on PLA and Cotton, Cellulose and Rice Straw, characterization of fiber-matrix interface

- EUROKOMPOZIT – Production and characterization of PP/Kenaf preforms with different matrix ratio (unfinished task from first semestar) and new Kenaf-PLA samples

- ICTM – Characterization of Natural fib. and NF composites (SEM, WAX)

- USKIM – Characterization of NF composites

- MOEPP – Collecting data from the relevant partners for preliminary  analysis of Composite Indicators for sustainability of eco-friendly composites

- STUDIO R – Design of interior partitioning panels and report on target properties and parameters of selected parts of eco-house

- IP-BAS – Kinetics and thermodynamic parameters of crystallization of PLA, POM, WAX, microhardness

- GEONARDO - Collecting data from the relevant partners for preliminary  analysis of Composite Indicators for sustainability of eco-friendly composites in cooperation with MOEPP

Short term task for each partner: Delivering of short report on the first six months activities performed in the framework of the project to the coordinator Dr.Avella and INCO-countries coordinator prof.G.Bogoeva-Gaceva- deadline 15.IV.2005.

Dissemination:

- Poster presentations at ECO-COMP 2005 Conference in Stocholm,Sweeden

- Two reviews include in the report and published

Next meeting:

29-30 September 2005, organizer CIDEMCO – Azpeitia, Spain

First Year Report:

At the end of October, 2005